## Sheet1
Risk_ID | Risk description | Impact description | Impact Level (1-5) | Probability Level (1-5) | Mitigation Notes | Status | Date Identified
Risk _ID_1 | Team Members availability | One of our Teammates is going to the militery by the next delivery It's not clear for us when will he come back | High | Critical | Will assign his task on 4 team members ( his task not determined yet ) | Open | 2026-03-28
Risk _ID_2 | Lack of Experience | The technicalities for building a website is not available in the team which might affect the output | Medium | Critical | Gaining more experience by practicing and the help of our coaches | Open | 2026-03-28
Risk _ID_3 | Time risk due to exams | Tight time table This might Cause stress and time pressure that will affect the progress | High | Major | We will time manage our tasks trying to fit the schedule | Open | 2026-03-28
Risk _ID_4 | AI risk | Not using AI , This might Cause stress and time pressure that will affect the progress | low | Minor | Not using AI Might cause coding problems | Open | 2026-03-28
Risk _ID_5 | Unstability of weather conditions (Poor connection) | This might Cause Delay in the tasks | Medium | Minor | Instead of online meetings we will reschedule offline meetings | Open | 2026-03-28
Risk _ID_6 | communication with customer | Not availability of customer most of the time it's hard to reach to the customer at any time | Medium | Major | Fixed scheduled meeting along the sprint that can't be changed or canceled | Open | 2026-03-28
Risk _ID_7 | AI competition | Having an AI competition that needs our development and Testing resources which may affect our progress | Medium | Major | We will time manage our tasks trying to fit the schedule | Open | 2026-03-29